BAG CRAFT

E-Commerce Platform

Full-Stack Development Roadmap

| Frontend Next.js 14 (App Router) | Backend Next.js API Routes | Database PostgreSQL + Prisma | Payments Paystack |
| --- | --- | --- | --- |

12 Pages  •  Full E-Commerce  •  6-Phase Build Plan

# 1. Project Overview

| Business | Bag production company — sells finished bags & offers training/courses |
| --- | --- |

| Goal | Full e-commerce website: browsing, cart, checkout, Paystack payment |
| --- | --- |

| Tech Stack | Next.js 14 (App Router) · TypeScript · Tailwind CSS · PostgreSQL · Prisma · Paystack |
| --- | --- |

| Hosting | Vercel (frontend/API) + Supabase or Railway (PostgreSQL) |
| --- | --- |

| Timeline | ~12–16 weeks across 6 phases (can overlap for speed) |
| --- | --- |

## 12 Pages to Build

| # | Page | Key Features |
| --- | --- | --- |
| 1 | Home Page | Hero banner, featured products, quick links to shop & training |
| 2 | About Us | Brand story, mission, team photos, values |
| 3 | Gallery / Portfolio | Grid of finished bags & students' work, filterable |
| 4 | Products Page | Product listing with filters, search, add-to-cart |
| 5 | Training / Courses | Course cards with enrolment CTA |
| 6 | Testimonials | Customer + trainee reviews, star ratings |
| 7 | Contact Page | Phone, email, map, contact form |
| 8 | Online Registration Form | Training sign-up linked to courses |
| 9 | Online Store / Cart | Cart drawer/page, quantity control, order summary |
| 10 | Checkout + Payment | Shipping details, Paystack inline payment |
| 11 | Blog / News Section | Articles, category tags, search |
| 12 | FAQ | Accordion-style answers, search |

# 2. Build Phases

The project is split into 6 sequential phases. Each phase ends with a working, testable deliverable so you can review progress before moving on.

| Phase 1: Foundation & Setup (Week 1–2) |  |  |
| --- | --- | --- |
| Task | Details | Deliverable |
| Next.js project init | Next.js 14, TypeScript, Tailwind CSS, ESLint, Prettier | Running dev server |
| Folder structure | app/, components/, lib/, prisma/, types/, hooks/ | Clean architecture |
| PostgreSQL setup | Supabase or Railway free tier, connection string | DB running in cloud |
| Prisma ORM | schema.prisma for User, Product, Order, Cart, Course, BlogPost | DB schema & migrations |
| Authentication | NextAuth.js — Google + email/password, role: customer / admin | Login & signup pages |
| Env variables | .env.local for DB, Paystack keys, NextAuth secret | Secrets secured |
| Deployment pipeline | Vercel project linked to GitHub, auto-deploy on push | Live staging URL |

| Phase 2: Core Pages (No E-Commerce) (Week 3–5) |  |  |
| --- | --- | --- |
| Task | Details | Deliverable |
| Home Page | Hero, featured products section (static), CTA banners | / route live |
| About Us | Brand story, team, mission — CMS-ready markdown or DB | /about live |
| Gallery / Portfolio | Image grid with lightbox, filterable by category | /gallery live |
| Testimonials | Static + DB-backed reviews with star ratings | /testimonials live |
| Contact Page | Contact form → email (Nodemailer/Resend), Google Maps embed | /contact live |
| Blog / News | Article list + single post page, category filter | /blog live |
| FAQ Page | Accordion component, search filter | /faq live |
| Shared layout | Navbar, footer, mobile menu, SEO meta tags | All pages use layout |

| Phase 3: Products & Shop (Week 6–8) |  |  |
| --- | --- | --- |
| Task | Details | Deliverable |
| Product DB + seed | Products table with name, price, images, stock, category | Products in DB |
| Products page | Grid layout, filter by category, sort by price, search | /products live |
| Product detail page | Image gallery, description, size/colour picker, Add to Cart | /products/[slug] |
| Cart system | Cart stored in DB (logged-in) or localStorage (guest), cart drawer | Cart works end-to-end |
| Cart page | Line items, quantity update, remove, subtotal, proceed to checkout | /cart live |
| Admin: Products | Protected /admin — add, edit, delete products, upload images | Admin CRUD ready |
| Image uploads | Cloudinary or Supabase Storage for product photos | Images stored & served |

| Phase 4: Checkout & Paystack (Week 9–10) |  |  |
| --- | --- | --- |
| Task | Details | Deliverable |
| Checkout page | Shipping address form, order summary, place order button | /checkout UI |
| Order creation | POST /api/orders — create pending order in DB | Order API working |
| Paystack integration | Paystack Inline JS popup, reference generation | Test payment works |
| Payment verification | Webhook: /api/webhooks/paystack — verify & update order status | Payments verified |
| Order confirmation | Success page with order ID, email receipt via Resend | /order/[id] live |
| Orders dashboard | Customer: view their orders + status; Admin: all orders list | Order tracking live |
| Stock management | Auto-reduce stock on payment success, show 'Out of Stock' | Inventory tracked |

| Phase 5: Training & Registration (Week 11–12) |  |  |
| --- | --- | --- |
| Task | Details | Deliverable |
| Courses page | Course cards: title, duration, price, level, enrol CTA | /training live |
| Course detail | Full description, curriculum, instructor bio, enrol button | /training/[slug] |
| Registration form | Name, phone, email, course choice, payment (Paystack) | /register live |
| Registration flow | Paystack payment → confirm enrolment → email confirmation | Full flow tested |
| Admin: Courses | Add/edit/delete courses, view enrolments | Course admin ready |
| Admin: Registrations | List of registered students per course | Enrolment list live |

| Phase 6: Polish, SEO & Launch (Week 13–16) |  |  |
| --- | --- | --- |
| Task | Details | Deliverable |
| SEO & metadata | Dynamic OG images, sitemap.xml, robots.txt, JSON-LD | SEO ready |
| Performance | Image optimisation (next/image), lazy loading, code splitting | Lighthouse > 90 |
| Mobile QA | Full responsive test on iOS & Android, touch interactions | Mobile perfect |
| Security audit | CSRF protection, rate limiting, SQL injection check, HTTPS | Secure |
| Analytics | Google Analytics 4 or Umami — track sales, page views | Analytics live |
| Admin dashboard | Revenue chart, top products, recent orders overview | /admin/dashboard |
| Final UAT | Full end-to-end test: browse → cart → pay → email receipt | Launch approved |
| Go live | Point custom domain, enable Paystack live keys, monitor | LIVE 🚀 |

# 3. Database Schema (Key Models)

All models live in prisma/schema.prisma. Here is the core structure:

- User id, name, email, passwordHash, role (CUSTOMER | ADMIN), createdAt

- Product id, name, slug, description, price, images[], stock, category, featured

- Cart id, userId (nullable for guests), items[CartItem]

- CartItem id, cartId, productId, quantity

- Order id, userId, status (PENDING | PAID | SHIPPED | DELIVERED), total, shippingAddress

- OrderItem id, orderId, productId, quantity, unitPrice

- Course id, title, slug, description, price, duration, level, instructor

- Enrolment id, userId, courseId, paymentRef, status

- BlogPost id, title, slug, content, category, publishedAt

- Testimonial id, authorName, content, rating, source (CUSTOMER | TRAINEE)

# 4. Recommended Folder Structure

| Path | Purpose |
| --- | --- |
| app/ | All pages and API routes (Next.js App Router) |
| app/(shop)/ | Public pages: home, products, cart, checkout |
| app/(auth)/ | Login, signup, forgot-password |
| app/admin/ | Protected admin dashboard |
| app/api/ | REST endpoints: orders, products, webhooks |
| components/ui/ | Reusable UI: Button, Card, Modal, Navbar, Footer |
| components/shop/ | ProductCard, CartDrawer, CheckoutForm |
| lib/prisma.ts | Prisma client singleton |
| lib/paystack.ts | Paystack helper functions |
| lib/auth.ts | NextAuth config |
| prisma/schema.prisma | All DB models |
| prisma/seed.ts | Seed script for demo data |
| public/ | Static assets, OG images |
| .env.local | Secrets (never commit to Git) |

# 5. Paystack Checkout Flow

Here is the exact sequence for a successful order on the platform:

| 1 | Customer fills checkout form | Shipping address + personal details collected client-side |
| --- | --- | --- |

| 2 | POST /api/orders | Server creates Order with status PENDING in PostgreSQL |
| --- | --- | --- |

| 3 | Paystack popup opens | Client-side: PaystackPop.setup({ email, amount, ref }) → opens modal |
| --- | --- | --- |

| 4 | Customer pays | Card/bank transfer/USSD handled entirely by Paystack |
| --- | --- | --- |

| 5 | Payment callback fires | onSuccess(reference) called in browser → server verifies |
| --- | --- | --- |

| 6 | POST /api/verify-payment | Server calls Paystack /transaction/verify/:ref — checks status |
| --- | --- | --- |

| 7 | Order updated to PAID | Stock reduced, order status set, Paystack ref saved |
| --- | --- | --- |

| 8 | Email receipt sent | Resend or Nodemailer fires order confirmation to customer |
| --- | --- | --- |

| 9 | Webhook (backup) | Paystack POSTs to /api/webhooks/paystack for extra reliability |
| --- | --- | --- |

# 6. Tools, Services & Costs

| Service | Purpose | Cost |
| --- | --- | --- |
| Vercel | Next.js hosting, CDN, serverless functions | Free (Hobby plan) |
| Supabase / Railway | Managed PostgreSQL database | Free tier available |
| Paystack | Payment gateway (NG focus, supports cards/USSD) | % per transaction |
| Cloudinary | Product image storage & transformation | Free up to 25GB |
| Resend / Nodemailer | Transactional emails (receipts, confirmations) | Free up to 3k/mo |
| NextAuth.js | Authentication (Google OAuth + email) | Open source, free |
| GitHub | Version control, CI/CD triggers | Free |
| Google Analytics 4 | User behaviour & sales tracking | Free |

# 7. How We Work Together

We tackle one phase at a time. At the end of each phase, you review the live staging URL and approve before we move to the next. Here is the workflow:

- Step 1: You confirm the phase to start (recommend Phase 1 first)

- Step 2: I generate all the code files with full explanations

- Step 3: You push to GitHub — Vercel auto-deploys to a staging URL

- Step 4: You test it, request changes, I iterate until approved

- Step 5: We move to the next phase

Each phase is self-contained — even if we pause, you always have a working site.

Ready to start? Just say: "Start Phase 1 — Foundation & Setup" and I will generate all the setup code, folder structure, Prisma schema, and authentication for your project.